# IU04 - Research Planning & Scheduling

Research Project (CPL) | RAG-Friendly Learning Material

Purpose: Help learners convert the research proposal into a realistic work plan using WBS, dependencies, milestones, scheduling, resources, and risk management.

# LM0401 - Research Project Plan

| Chunk ID | LM0401 |
| --- | --- |
| Title | Research Project Plan |
| Learning Objective | Understand the role of a research project plan. |
| Content | A research project plan translates the approved research idea into organised activities, responsibilities, resources, dates, and expected outputs. It should show how the learner will move from proposal through data collection, analysis, reporting, and reflection. |
| Example | A plan for an AI chatbot study may include literature review, questionnaire design, ethics preparation, data collection, analysis, recommendations, report writing, and presentation. |
| Key Takeaways | A plan connects objectives to actions; activities should be realistic and sequenced; progress should be reviewable. |
| Metadata | Document Type: Learning Material Module: Research Project (CPL) Instructional Unit: IU04 - Research Planning & Scheduling Section: Project Planning Topic: Research Project Plan Source: Official Learning Material Audience: Learner Intent: Explain / Guide Difficulty: Beginner Version: 1.0 |
| Question | What should be included in my research project plan? |
| Keywords | research plan, project plan, activities, deliverables |

# LM0402 - Work Breakdown Structure (WBS)

| Chunk ID | LM0402 |
| --- | --- |
| Title | Work Breakdown Structure (WBS) |
| Learning Objective | Break a research project into manageable work packages and tasks. |
| Content | A Work Breakdown Structure divides the overall project into smaller deliverables, activities, and tasks. The decomposition should be detailed enough to estimate effort, assign responsibility, monitor progress, and identify dependencies without becoming an unnecessary list of tiny actions. |
| Example | Research Project → Proposal → Literature Review → Methodology → Data Collection → Analysis → Findings → Recommendations → Reflection → Final Submission. |
| Key Takeaways | Break work into manageable units; organise around deliverables; use the WBS as the foundation for scheduling. |
| Metadata | Document Type: Learning Material Module: Research Project (CPL) Instructional Unit: IU04 - Research Planning & Scheduling Section: WBS Topic: Work Breakdown Structure (WBS) Source: Official Learning Material Audience: Learner Intent: Explain / Guide Difficulty: Beginner Version: 1.0 |
| Question | What is a Work Breakdown Structure? |
| Keywords | WBS, work breakdown structure, tasks, work packages |

# LM0403 - Task Dependencies

| Chunk ID | LM0403 |
| --- | --- |
| Title | Task Dependencies |
| Learning Objective | Identify relationships between research activities. |
| Content | A dependency exists when one activity relies on another. Finish-to-start relationships are common in research: for example, data analysis normally cannot be completed until relevant data has been collected. Recognising dependencies prevents unrealistic scheduling and helps identify activities that could delay later work. |
| Example | The questionnaire should be designed and checked before it is distributed; data collection should be substantially complete before final quantitative analysis begins. |
| Key Takeaways | Sequence tasks logically; identify prerequisites; dependencies affect the schedule and project risk. |
| Metadata | Document Type: Learning Material Module: Research Project (CPL) Instructional Unit: IU04 - Research Planning & Scheduling Section: Dependencies Topic: Task Dependencies Source: Official Learning Material Audience: Learner Intent: Explain / Guide Difficulty: Beginner Version: 1.0 |
| Question | What are task dependencies in a research project? |
| Keywords | task dependency, sequencing, prerequisite, schedule |

# LM0404 - Milestones and Deliverables

| Chunk ID | LM0404 |
| --- | --- |
| Title | Milestones and Deliverables |
| Learning Objective | Distinguish important checkpoints from project outputs. |
| Content | A deliverable is a tangible output such as a proposal, questionnaire, analysed dataset, report, or presentation. A milestone is a significant checkpoint used to monitor progress, such as proposal approval or completion of data collection. Milestones usually have zero duration in a schedule. |
| Example | Deliverable: completed literature review. Milestone: literature review approved and methodology ready to begin. |
| Key Takeaways | Deliverables are outputs; milestones are checkpoints; both should connect to the project objectives. |
| Metadata | Document Type: Learning Material Module: Research Project (CPL) Instructional Unit: IU04 - Research Planning & Scheduling Section: Milestones Topic: Milestones and Deliverables Source: Official Learning Material Audience: Learner Intent: Explain / Guide Difficulty: Beginner Version: 1.0 |
| Question | What is the difference between a milestone and a deliverable? |
| Keywords | milestone, deliverable, checkpoint, output |

# LM0405 - Gantt Chart

| Chunk ID | LM0405 |
| --- | --- |
| Title | Gantt Chart |
| Learning Objective | Use a Gantt chart to communicate the project schedule. |
| Content | A Gantt chart displays project activities against time. It can show start and finish dates, durations, overlap, dependencies, milestones, and progress. The chart should reflect the WBS and be updated when significant changes occur rather than being created only for submission. |
| Example | A 10-week research project might schedule literature review in Weeks 1–3, methodology in Weeks 2–4, data collection in Weeks 4–6, analysis in Weeks 6–7, and reporting in Weeks 7–10. |
| Key Takeaways | Build the Gantt chart from the WBS; show realistic timing and overlap; update it when the plan changes. |
| Metadata | Document Type: Learning Material Module: Research Project (CPL) Instructional Unit: IU04 - Research Planning & Scheduling Section: Gantt Chart Topic: Gantt Chart Source: Official Learning Material Audience: Learner Intent: Explain / Guide Difficulty: Beginner Version: 1.0 |
| Question | How do I use a Gantt chart for my research project? |
| Keywords | Gantt chart, timeline, schedule, duration |

# LM0406 - Time Estimation

| Chunk ID | LM0406 |
| --- | --- |
| Title | Time Estimation |
| Learning Objective | Estimate realistic durations for research activities. |
| Content | Time estimation considers the effort required, availability of participants and resources, review or approval delays, and uncertainty. Learners should allow contingency rather than assuming every activity will finish at the earliest possible date. |
| Example | If survey collection is expected to take one week, allocating additional time for low response rates can reduce the risk of delaying analysis. |
| Key Takeaways | Estimate based on actual work and access; include contingency; revisit estimates when evidence changes. |
| Metadata | Document Type: Learning Material Module: Research Project (CPL) Instructional Unit: IU04 - Research Planning & Scheduling Section: Time Estimation Topic: Time Estimation Source: Official Learning Material Audience: Learner Intent: Explain / Guide Difficulty: Beginner Version: 1.0 |
| Question | How should I estimate time for research tasks? |
| Keywords | time estimation, duration, contingency, planning |

# LM0407 - Resources and Responsibilities

| Chunk ID | LM0407 |
| --- | --- |
| Title | Resources and Responsibilities |
| Learning Objective | Identify resources required to complete the research. |
| Content | Research resources may include people, software, hardware, datasets, academic databases, survey platforms, meeting access, and budget. Responsibilities should clarify who performs or approves important activities, even when the learner is responsible for most project work. |
| Example | Resources for sentiment analysis research might include journal databases, survey software, spreadsheet or statistical tools, sample review data, and mentor feedback. |
| Key Takeaways | Identify resources before execution; check access and cost; connect resources to specific tasks. |
| Metadata | Document Type: Learning Material Module: Research Project (CPL) Instructional Unit: IU04 - Research Planning & Scheduling Section: Resources Topic: Resources and Responsibilities Source: Official Learning Material Audience: Learner Intent: Explain / Guide Difficulty: Beginner Version: 1.0 |
| Question | What resources do I need for my research project? |
| Keywords | resources, responsibility, software, data access |

# LM0408 - Project Risk Planning

| Chunk ID | LM0408 |
| --- | --- |
| Title | Project Risk Planning |
| Learning Objective | Plan responses to events that could disrupt the research. |
| Content | Risk planning identifies possible events, assesses their likelihood and impact, and defines actions to reduce or respond to them. Common research risks include low participant response, delayed approval, inaccessible data, technical failure, scope growth, and insufficient time. |
| Example | Risk: fewer survey responses than planned. Mitigation: distribute early, use reminders, and prepare an alternative evidence source. |
| Key Takeaways | Identify risks before they occur; assess likelihood and impact; define practical mitigation and contingency actions. |
| Metadata | Document Type: Learning Material Module: Research Project (CPL) Instructional Unit: IU04 - Research Planning & Scheduling Section: Risk Planning Topic: Project Risk Planning Source: Official Learning Material Audience: Learner Intent: Explain / Guide Difficulty: Beginner Version: 1.0 |
| Question | How do I manage risks in my research project plan? |
| Keywords | risk register, likelihood, impact, mitigation, contingency |

# LM0409 - Monitoring and Updating the Plan

| Chunk ID | LM0409 |
| --- | --- |
| Title | Monitoring and Updating the Plan |
| Learning Objective | Use the plan as an active project-control tool. |
| Content | Progress should be compared with the planned schedule throughout the project. When tasks are delayed or assumptions change, the learner should record the change, assess its effect on later activities, and revise the schedule or scope where appropriate. |
| Example | If participant recruitment takes one week longer, the learner may revise analysis dates while protecting the final reporting deadline. |
| Key Takeaways | Monitor actual versus planned progress; document significant changes; adapt while preserving research objectives. |
| Metadata | Document Type: Learning Material Module: Research Project (CPL) Instructional Unit: IU04 - Research Planning & Scheduling Section: Monitoring Topic: Monitoring and Updating the Plan Source: Official Learning Material Audience: Learner Intent: Explain / Guide Difficulty: Beginner Version: 1.0 |
| Question | What should I do if my research project falls behind schedule? |
| Keywords | monitoring, schedule update, progress, delay |

# LM0410 - IU04 Learning Check

| Chunk ID | LM0410 |
| --- | --- |
| Title | IU04 Learning Check |
| Learning Objective | Confirm that the project is ready for execution. |
| Content | Before beginning substantial data collection, the learner should have a WBS, logical task sequence, milestones, deliverables, realistic schedule, required resources, key risks, and a method for monitoring progress. |
| Example | The learner should be able to explain not only when each activity occurs but why the sequence and duration are realistic. |
| Key Takeaways | A useful plan is traceable from objectives to tasks, schedule, resources, risks, and outputs. |
| Metadata | Document Type: Learning Material Module: Research Project (CPL) Instructional Unit: IU04 - Research Planning & Scheduling Section: IU04 Summary Topic: IU04 Learning Check Source: Official Learning Material Audience: Learner Intent: Explain / Guide Difficulty: Beginner Version: 1.0 |
| Question | What should be completed in my research project plan? |
| Keywords | IU04 summary, WBS, Gantt chart, research planning checklist |